## Sheet1
Date | Tasks done | hours
2024-11-18 | plan begun - main themes and reference images, git/admin stuff, scrolling menu implemented | 6
2024-11-19 | combat implementation - basic parts and placeholder sprites/abiklities | 6
2024-11-20 | combat bugfixes and extra features | 5
2024-11-21 | Movement and dialogue system | 7
2024-11-22 | Impoved dialogue system and added decision support | 6
2024-11-25 | Finished dialogue system functionality & worked on some frontend stuff | 6
2024-11-26 | Some more front end for dialogue and a beginning on the inventory. | 3
2024-11-27 | Redoing backend for ui controllers so its easier to use. And some frontend for the movement system. | 6
2024-11-28 | item inventory done, and more front end for both dialogue and te rest of the inventory | 5
2024-11-29